ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Relevant country background	2

1.4.	Current state of affairs in the relevant sector	2

1.5.	Related programmes and other donor activities:	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	3

2.2.	Purpose	3

2.3.	Results to be achieved by the Consultant	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project intervention	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	5

4.2.	Specific activities	5

4.3.	Project management	6

5.	LOGISTICS AND TIMING	6

5.1.	Location	6

5.2.	Commencement date & Period of implementation of tasks	6

6.	REQUIREMENTS	6

6.1.	Personnel	6

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the Consultant	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission & approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Beneficiary country

OECS member states;  Anguilla, Antigua, Dominica, Grenada, Montserrat, St. Kitts & Nevis, St. Lucia, St. Vincent and BVI

## Contracting Authority

OECS/Export Development Unit

## Relevant country background

The overall development objective(s) of the Caribbean Trade and Private Sector Development Project (CTPSDP) under which this activity is funded is to contribute to the gradual integration of CARIFORUM and OECS countries into the world economy through regional economic integration and the strategic repositioning of the region’s economies through private sector development and in turn to enhance regional economic growth and thus help to alleviate poverty.

## Current state of affairs in the relevant sector

The Caribbean Trade and Private Sector Development Program (CTPSDP) establishes the rationale for the Programme as it cites the Cotonou Agreement and its main objectives of poverty reduction and sustainable development through actions that can generate economic growth and develop the private sector and increase employment. Its successor the Economic Partnership Agreement, more recently established between EC and Cariforum, gives further support to those objectives and the promotion of regional integration as it offers opportunities for access to the EC markets and innovation programmes.

Further a number of regional policy measures have been articulated in initiatives such as Cariforum Regional Integration and Development Strategy and the Caribbean Regional Indicative Programme that indicate actions that will address the expansion of the regional economic bases, the integration of an expanded regional space and the repositioning of the Caribbean on the global economy.

The Caribbean Single Market and Economy and the OECS Economic Union are most relevant actions in an advanced stage of implementation. It is in this context that the purpose of 9th EDF CTPSDP is of particular relevance as it focuses on private sector development and competitiveness and responds to the market opportunities and challenges that are emerging.

It is in his context that this training programme is geared to equip SMEs with the management skills required to effectively manage their business which will inturn strengthen capacity and competitiveness.

## Related programmes and other donor activities:

The EDU has been delivering programmes to OECS companies jointly with the CDE and Proinvest in management, product development, product quality and safety and marketing.   All these projects will directly complement activities proposed under this contract.

Linkages with other initiatives in trade and SME competitiveness being supported by USAID and CIDA in particular will be strengthened and synergies with the CTPSD Programme effected.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To equip OECS/EDU client companies and business support organizations personnel with the Business Management tolls in Costing and Pricing, Marketing, Records management and Human Resource Management Skills to successfully manage their business for the competitive export market.

## Purpose

The purpose of this contract is as follows:

Deliver seven (7) national workshops in OECS member states on Human Resource Management, Marketing to Suit Your Business and Costing and Pricing.

## Results to be achieved by the Consultant

The results to be achieved are as  follows:

- Design the workshop programme to be highly participative and interactive

- Deliver seven (7) national workshops in the above listed OECS member states

- Be available for one on one discussions and assistance with participants

- Prepare a detailed training manual of the workshop which can be used as a reference guide for participants.

- Prepare a summary report of the workshop to include participants evaluation

- Prepare an electronic version of the workshop which can be made available to EDU client companies.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project intervention

Projected results, activities and assumptions were developed from inputs by the OECS/EDU Programme Management team and proposals submitted by EDU clients.

The achievement of targets is largely contingent on the assumptions listed, particularly the existence of a sound macro-economic framework, the financial counter parting of client companies and exogenous factors such as the occurrence of natural disasters.

## Risks

The risks associated with the intervention are as follows:

- Lack of participation by the selected client companies.

- Major  catastrophic natural disasters

- Sudden political instability,

- External global shocks

- Non approval of the EDU PE 3

# SCOPE OF THE WORK

## General

### Description of the assignment

Deliver seven (7) national workshops in OECS member states on Human Resource Management, Marketing to Suit Your Business and Costing and Pricing.

The assignment is divided into Lots, consultants can bid on an individual lot or on all three lots.   The global budget quoted comprises the following :

- The contract will cover the Consultant’s costs     -   EC$ 127,800.00

- The EDU will cover the other logistics and workshop costs  -

EC$ 135,895.00

## Specific activities

The consultant (s) will be required to deliver seven (7) national workshops in the Human Resource Management, Marketing to Suit Your Business and Costing & Pricing.   The course content of the workshop should include but is not limited to the following topics:

- Introduction and development of a simple costing and pricing tool/method

- Introduction to the concept of reviewing company systems/method and identifying its strengths and weaknesses

- Introducing a simple book-keeping/accounting system suitable to the company’s capacity

- Computing break even

- How to develop a detailed costing and pricing structure for existing goods and services

- Principles of Marketing, Records management and Human Resource Management

- Introduction to various forms of e-commerce to increase performance

- Hot to prepare an effective marketing Plan, Records Management Plan and Human Resource Strategy

- The overall effects of Costing and Pricing, marketing, Records management and HR Management on the bottom line.

- Design the workshop program to be highly interactive and participative

- Be available for one on one discussions and provide assistance to participants during and at least four weeks after the training programme.

- Provide a training manual that can be used as a reference guide for participants.

- Participate in the development of an electronic training version of the workshop

## Project management

### Responsible body

OECS/EDU will be responsible for managing the contract

### Management structure

The Consultant hereby agrees to perform the services detailed in this contract under the direction of the Head of Unit of OECS/EDU and the Business Development Officer and any such other personnel who may be assigned;

### Facilities to be provided by the Contracting Authority

Training facility and other logistic requirements

# LOGISTICS AND TIMING

## Location

EDU Offices, Roseau, Dominica

## Commencement date & Period of implementation of tasks

The intended commencement date is July 19th 2010 and the period of implementation of the contract will be three (3) months from this date. Please refer to Articles 4 and 5 of the Special Conditions for the actual commencement date and period of implementation.

It is the intention of the EDU depending on the outcome of this initial contract that a second phase may be initiated which will provided targeted inplant support to companies.

# REQUIREMENTS

## Personnel

### Key experts

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert (s)

The individual (s) conducting the workshop should possess the following qualifications as per the subject areas to be delivered.

Qualifications and Skills

Human Resource Management - Minimum Bachelors Degree in HR Management/Business Management or  post graduate training in HR Management and experience in conducting similar workshops.

Marketing to Suit - Minimum Bachelors Degree in Marketing/International Business Relations or Business Management or  post graduate training in Marketing/International Business Relations and experience in conducting similar workshops.

Costing and Pricing - Minimum Bachelors Degree in Finance/Business Management with experience in cost accounting and  inventory, or  post graduate training in Financial Management and experience in conducting similar workshops.

General Experience

Experience in the delivery of workshops and in the areas of HR Management, Marketing and Costing and Pricing.

Specific Experience

Experienced in the specific discipline as listed in above in the qualification and skills and in the production of training manuals.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender. The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

## Office accommodation

The Consultant shall ensure that experts are adequately supported and equipped. In particular it shall ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support its activities under the contract and to ensure that its employees are paid regularly and in a timely fashion.

The contracting authority will be responsible for the duplication of the workshop manuals, the

cost for conference facility, the cost of the electronic training tool and other logistics.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / beneficiary country as part of this service contract or transferred to the Contracting Authority at the end of this contract. Any equipment related to this contract which is to be acquired by the beneficiary country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The consultant will submit the following reports in English in two original and one (1) electronic  copy:

- Final Report of maximum twelve (12) pages to be produced after each workshop one week from the commencement of the implementation. In the report the consultant shall describe e.g. the events undertaken in the implementation of the activity, findings, the constraints encountered in delivering the workshop, the encountered and/or foreseen difficulties in addition to the workshop. The consultant is advised to proceed with his/her work also in absence of comments by the Contracting Authority to the final report.

## Submission & approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

- The successful completion of seven workshops,

- The full participation of EDU client companies and BSOs

- The completed evaluation forms by partiicpants

## Special requirements

Not applicable