ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Relevant country background	2

1.4.	Current state of affairs in the relevant sector	2

1.5.	Related programmes and other donor activities:	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	4

2.2.	Purpose	4

2.3.	Results to be achieved by the Consultant	4

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project intervention	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	5

4.1.	General	5

4.2.	Specific activities	6

4.3.	Project management	7

5.	LOGISTICS AND TIMING	7

5.1.	Location	7

5.2.	Commencement date & Period of implementation of tasks	7

6.	REQUIREMENTS	7

6.1.	Personnel	7

6.2.	Office accommodation	8

6.3.	Facilities to be provided by the Consultant	8

6.4.	Equipment	8

7.	REPORTS	9

7.1.	Reporting requirements	9

7.2.	Submission & approval of reports	9

8.	MONITORING AND EVALUATION	9

8.1.	Definition of indicators	9

8.2.	Special requirements	9

# BACKGROUND INFORMATION

## Beneficiary country

OECS member states;  Anguilla, Antigua, Dominica, Grenada, Montserrat, St. Kitts & Nevis, St. Lucia, St. Vincent and BVI

## Contracting Authority

OECS/Export Development Unit

## Relevant country background

The overall development objective(s) of the Caribbean Trade and Private Sector Development Project (CTPSDP) under which this activity is funded is to contribute to the gradual integration of CARIFORUM and OECS countries into the world economy through regional economic integration and the strategic repositioning of the region’s economies through private sector development and in turn to enhance regional economic growth and thus help to alleviate poverty.

## Current state of affairs in the relevant sector

The Caribbean Trade and Private Sector Development Program (CTPSDP) establishes the rationale for the Programme as it cites the Cotonou Agreement and its main objectives of poverty reduction and sustainable development through actions that can generate economic growth and develop the private sector and increase employment. Its successor the Economic Partnership Agreement, more recently established between EU and Cariforum, gives further support to those objectives and the promotion of regional integration as it offers opportunities for access to the EU markets and innovation programmes.

Further a number of regional policy measures have been articulated in initiatives such as Cariforum Regional Integration and Development Strategy and the Caribbean Regional Indicative Programme that indicate actions that will address the expansion of the regional economic bases, the integration of an expanded regional space and the repositioning of the Caribbean on the global economy.

The Caribbean Single Market and Economy and the OECS Economic Union are most relevant actions in an advanced stage of implementation. It is in this context that the purpose of 9th EDF CTPSDP is of particular relevance as it focuses on private sector development and competitiveness and responds to the market opportunities and challenges that are emerging.

It is in his context that this training programme is geared to equip SMEs with the management skills required to effectively manage their business which will inturn strengthen capacity and competitiveness.

## Related programmes and other donor activities:

The EDU has been delivering programmes to OECS companies jointly with the CDE and Proinvest in management, product development, product quality and safety and marketing.   All these projects will directly complement activities proposed under this contract.

Linkages with other initiatives in trade and SME competitiveness being supported by USAID and CIDA in particular will be strengthened and synergies with the CTPSD Programme effected.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To conduct an Audit of the OECS EDU clients in the Arts & Craft Sector, and to develop a technical assistance plan and strategy for the increase competitiveness of the products, including the identification of potential markets for the products.

## Purpose

The purpose of this contract is as follows:

Conduct of diagnostic review of EDU clients in the Arts & Craft Sector in all nine of the OECS member territories to establish the present status of the sector; research on potential markets for the products, and development of a strategic plan which will provide the OECS/EDU with critical information in order to develop relevant programmes geared at increasing the competitiveness of the sector.

## Results to be achieved by the Consultant

The results to be achieved are as follows:

- Produce nine (9) Country Reports in respect of all the OECS territories detailing the findings from the Diagnostic Review of the EDU Clients firms and the sector in general including action plans for the member territories.

- Develop a Technical Assistance Plan, which will be used to provide support to the firms.

- Develop a Strategic Plan for the Arts & Craft Sector in the OECS for the next 5 years;

# ASSUMPTIONS & RISKS

## Assumptions underlying the project intervention

Assumptions made:

- The clients of the OECS EDU are representative of the Arts & Craft Sector in the OECS and thereby the audit of the clients will provide information on the current status of the sector in general and will provide sufficient insight into the sector.

- Proper records are maintained by the EDU clients in the Arts & Craft Sector.

- The EDU clients in the Arts & Craft Sector will fully participate in the exercise and provide the consultant with all the necessary information required from the sector in a timely manner.

The achievement of targets is largely contingent on the assumptions listed, particularly the existence of a sound macro-economic framework of the sector and the full participation of client companies.

## Risks

The risks associated with the intervention are as follows:

- Non approval of the EDU PE 3

- Lack of participation by the client firms.

- Lack of proper records held by client firms

- Major  catastrophic natural disasters

- Sudden political or social instability,

# SCOPE OF THE WORK

## General

### Description of the assignment

Conduct of diagnostic review of OECS EDU Arts & Craft clients and analysis of the Arts & Craft Sector in the OECS, and providing strategic direction for the sector.

The global budget quoted is EC$ 105,100.00 which includes consultant fees, airfare and perdiem and associated costs

## Specific activities

The consultant (s) will be required to conduct diagnostic review of OECS EDU clients in the Arts & Craft Sector in all nine member territories of the OECS and develop nine (9) country reports of findings, a strategic plan and an action plan/technical assistance plan. The consultancy should include but is not limited to the following:

  - Conduct an analysis and diagnostic review of EDU clients in the Arts & Crafts Sector to determine the sector’s current status and contribution it is making to the economies of the OECS. The diagnostics review to include the following:

    - Conduct Financial Assessment – In-plant assessment and evaluation of the firm’s bookkeeping & Accounting, and Credit and Collection procedures;

    - Conduct Sales and Marketing Assessment – Pricing Structure, Market Research, Market Planning and sales Management;

    - Conduct Production and Operational Assessment – Staffing, Inventory Management, Plant Layout, Process Flow; Standards / & Certification;

    - Conduct Management and Leadership Assessment – Planning Procedures, Decision Making, Executive Supervision, and Job Training;

    - Conduct Strategic Planning Assessment to include Company Policies, Profitability, Sales Growth,

  - Conduct visits and interviews (in plant and via the telephone) with OECS EDU Clients in the Arts and Crafts sectors with a view to identifying the clients’ needs, expectations, major constraints, existing challenges and opportunities.

  - Conduct meetings with key stakeholders.

  - Research constraints facing the sector to include: raw material availability; imported inputs; shipping; packaging; product treatment & certification; etc.

  - Research the trade industry - defining the current market for the craft products (high end products, mass production, etc.).

  - Prepare a country report (national focus) for each of the nine (9) OECS islands detailing the findings from the assessment and evaluation of the sector in that country; providing recommendations and an action plan for the growth and development of the sector.

  - Develop a technical assistance plan for the sector (regional focus– OECS) geared at targeted areas of needs.

  - Develop a 5-year strategic plan for the sector (regional focus– OECS) detailing findings from the diagnostic review; findings from meetings, plant visits and telephone calls; the analysis and status of the sector in general; and the contribution of the sector to the economies of the OECS. The plan should provide recommendations geared towards increasing the sector’s competitiveness and access to potential markets.

## Project management

### Responsible body

OECS/EDU will be responsible for managing the contract

### Management structure

The Consultant hereby agrees to perform the services detailed in this contract under the direction of the Head of Unit of OECS/EDU and the Business Development Officer and any such other personnel who may be assigned;

### Facilities to be provided by the Contracting Authority

Meeting facility and other logistic requirements

# LOGISTICS AND TIMING

## Location

EDU Offices, Roseau, Dominica

## Commencement date & Period of implementation of tasks

The intended commencement date is July 26, 2010 and the period of implementation of the contract will be three (3) months from this date. Please refer to Articles 4 and 5 of the Special Conditions for the actual commencement date and period of implementation.

# REQUIREMENTS

## Personnel

### Key experts

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key Expert 1 – Team Leader

Qualifications and Skills

Minimum - Bachelor’s Degree in Business Management /Accounting /Finance /Marketing or related field or post graduate studies in related field; and experience in consultancy work of a similar nature;

General Experience

Experience in consultancy work of a similar nature,

Specific Experience

Experienced in the specific discipline as listed above in the qualification, and knowledge and experience in the Arts & Craft Sector and/or Design knowledge and skills would be an asset.

Key Expert  2

Qualifications and Skills

Minimum - Bachelor’s Degree in Business Management /Accounting /Finance /Marketing or related field;

General Experience

Experience in consultancy work of a similar nature,

Specific Experience

Experienced in the specific discipline as listed in above in the qualification, and knowledge and experience in the Arts & Craft Sector and/or research work would be an asset.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender. The Consultant shall select and hire other experts as required according to the needs. The selection procedures used by the Consultant to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Cost for backstopping and support staff, as needed, are considered to be included in the financial offer of the tenderer.

## Office accommodation

The Consultant shall ensure that experts are adequately supported and equipped. In particular it shall ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support its activities under the contract and to ensure that its employees are paid regularly and in a timely fashion.

The contracting authority will be responsible for the cost for meeting facility and other logistics.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / beneficiary country as part of this service contract or transferred to the Contracting Authority at the end of this contract. Any equipment related to this contract which is to be acquired by the beneficiary country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The consultant will submit the following reports in English in two original and one (1) electronic copy:

- Final Reports A – Country Reports including an Action Plan for each of all the nine (9) member territories to be produced after completion of all the island’s visits two weeks after the conclusion of the last visit. In the report, the consultant shall describe e.g. the events undertaken in the implementation of the activity and the findings and the constraints encountered in conducting the audit.

- Final Reports B – A Technical Assistance Plan to equip the OECS EDU with pertinent information of areas of critical need by the sector, as well as identification of sources of assistance.

- Final Reports C - A 5-year Strategic Plan providing the OECS EDU with clear guidance and direction for the sector in order to address the issues faced by the sector and to guide and facilitate the formulation of programmes towards enhancing the sector’s competitiveness and market penetration.

- The consultant is advised to proceed with his/her work also in absence of comments by the Contracting Authority to the final report.

## Submission & approval of reports

The reports referred to above must be submitted to the Project Manager (Business Development Officer) identified in the contract. The Project Manager (Business Development Officer) is responsible for approving the reports; final approval will be made by the Head of Unit, OECS/EDU.

# MONITORING AND EVALUATION

## Definition of indicators

- The successful completion of the audit of the Arts & Craft Clients in all nine OECS member territory,

- The full participation of EDU client firms,

- The Business Development Officer’s activity report.

## Special requirements

Not applicable